## Scoring
Ladenford Den Risk Log
Girlguiding Angus
Note 1
Table 1 - Likelihood definitions
Score | Description | Chance of occurrence
1 | Rare | Very little evidence to assume this event would happen – will only happen in exceptional circumstances
2 | Unlikely | Not expected to happen, but definite potential exists – unlikely to occur.
3 | Possible | Has happened before on occasions – reasonable chance of occurring
4 | Likely | Strong possibility that this could occur – likely to occur
5 | Almost certain | This is expected to occur frequently / in most circumstances
Table 2 - Impact descriptions
Score | Description
1 | Negligible
2 | Minor
3 | Moderate
4 | Major
5 | Extreme
For each category you should consider any potential risks and complete the schedule. The columns to be completed are:
Risk Area | A description of what the risk is and what any outcomes would be
Likelihood (L) | How likely is it the risk will occur
Impact (I) | If the risk did occur how would it impact the County
Inherent Risk (IH) | A score will be calculated based on L X I
Controls | Record any controls in place to manage the Inherent Risk
Likelihood (L) | Rescore the likelihood taking into account the controls
Impact (I) | Rescore the impact taking into account the controls
Managed Risk (MR) | A score will be calculated based on L x I
Actions 2023 | Record any action to be taken during the year to address the risk
Who | Record who will carry out these actions
Review | Record when the risk will be reviewed
Please note that the Inherent Risk column (IH) and the Manager Risk column (MR), highlighted in yellow, will be calculated automatically.
The scores given for Likelihood and Impact should be assessed from 1 – 5, with 1 being low and 5 being high.
Once the score has been calculated for the Managed Risk (MR) it will be assigned a colour based on the score. This will be:
Green | score between 1 – 15 |  | The risk is low
Amber | score between 16 – 19 |  | The risk is medium
Red | score 20 or above |  | The risk is high
This colour coding will allow the trustees to identify the high and medium risks and prioritise managing these.
The risk register should be reviewed and revised on a regularly basis.

## Finance
| Risk Area | L | I | IR | Controls already in place | L | I | MR | Actions 2026/7 | Who | Review | COMMENTS
FINANCE
1 | Loss of income due to reduced number of bookings | 4 | 3 | 12 | Property is advertised for use on the county website and is open to other youth organisations. | 3 | 3 | 9 | Ensure that all units in the area are aware of the facilities available. Site is also open to other youth organisations, ensure they are aware of availability in order to maximise income. | Ladenford Den Committee | Every Meeting
2 | County cannot afford the upkeep of Ladenford Den | 3 | 4 | 12 | A planned preventative maintenance schedule is in place to try and avoid emergency costly repairs | 3 | 3 | 9 | Maintenance schedule is in place to distribute expenditure over a number of years so that income is available to cover the costs. Income to be reviewed annually. | Ladenford Den Committee | 2026-10-01
3 | Ensure adequate insurance is in place for Ladenford Den | 2 | 5 | 10 | Insurance requirement is reviewed annually when policy is renewed | 2 | 3 | 6 | Ensure any changes to the property /grounds /equipment are taken into account in the insurance cover sought and put in place. | County Treasurer | 2026-10-01 | Property revalued October 2025.

## Governance
| Risk Area | L | I | IR | Controls already in place | L | I | MR | Actions 2026/7 | Who | Review | COMMENTS
GOVERNANCE
4 | Failure of Ladenford Den Committee to have adequate knowledge Girlguiding policies to reflect good practice | 3 | 3 | 9 | All members of Ladenford Den Committee are well inducted into their roles and knowledge is kept up to date regularly. | 2 | 3 | 6 | Ensure all Ladenford Den Committee members are aware of GGS guidance and where to find it. | Chair of LD | Annually | Property guidance can be found here: https://www.girlguidingscotland.org.uk/resource-county-category/finance-property-and-staff/
5 | Failure to have adequate knowledge and processes in place to reflect good practice with regard to management of the property | 3 | 3 | 9 | Support for property management can be found on the Girlguiding Scotland website here: https://www.girlguidingscotland.org.uk/resource-county-category/finance-property-and-staff/ | 2 | 3 | 6 | Any issues arising which require specialist property knowledge will be referred to Girlguiding Scotland's property group as required. | Chair of LD | Annual or as required | Contact property@girlguiding-scot.org.uk for specific questions
6 | Failure to recruit volunteers to support the running of Ladenford Den leading to lack of volunteer capacity to support safe and effective management | 3 | 3 | 9 | Look actively for new volunteers | 2 | 3 | 6 | Existing process will continue with open recruitment, defined role descriptions and induction process. Role descriptions required for members, secretary and treasurer. Look at users to idedntify potential nedw committee members as well as advertising more widely, and to non-members for appropriate roles if required. | Chair of LD | Annually or should volunteer numbers on the Committee drop

## Operational
| Risk Area | L | I | IR | Controls already in place | L | I | MR | Actions 2026/7 | Who | Review | COMMENTS
OPERATIONAL
7 | Slips and trips | 4 | 2 | 8 | Handrails in place at all steps. Steps painted with anti-slip deck paint (Aug 21) Veranda painted with anti-slip deck paint (Aug 21) Adults advised not to use shutter steps if alone. Wet floor sign to be used if floor is wet to warn others. Grass cutting contract in place to ensure campsite grass is not too long. | 3 | 2 | 6 | Veranda / steps - requirement for repainting to be undertaken 2025. Grass - contract for 10 cuts p.a. renewed annually. | Ladenford Den Committee | Annually in April | Still awaiting Criminal Justice Services undertaking this work asap midweek when site is empty.
8 | Working at Height | 3 | 3 | 9 | In campstore only use fixed access ladder. Users advised not to work alone at height. | 2 | 3 | 6 | On-going regular inspection of ladder. | Ladenford Den Committee | Monthly
9 | Camp fires | 3 | 3 | 9 | On campsite fires only allowed in designated areas and users advised that buckets of water should always be present. Fire extinguisher and sand buckets are in campstore. | 3 | 2 | 6 | Annual Inspection of fire extinguishers - Ramsay Fire | Ladenford Den Committee | Annually in June
10 | Electrics | 3 | 3 | 9 | Manuals for electrical equipment available to all hall users. All electrical items to be switched off when not in use. Strimmer only to be used by adults. Users advised to use extension leads only when essential and to fully unwind when using as per manufacturers instructions. | 3 | 2 | 6 | Annual Review | Ladenford Den Committee | Annually in April
11 | Water systems and legionella | 3 | 3 | 9 | Scottish Water survey done in 2017 and procedures agreed. Water system drained down in winter to safeguard against burst pipes. | 3 | 2 | 6 | Procedure in place for legionella testing on a monthly basis. Cleaners to sterilize shower heads on a quarterly basis. | Ladenford Den Committee | Annually in April
12 | Tables and Chairs | 3 | 3 | 9 | Users advised to stack chairs no more than 6 high and tables lengthways to avoid toppling. | 3 | 2 | 6 | Annual review. | Ladenford Den Committee | Annually in April
13 | Control of vermin | 3 | 3 | 9 | Ladenford Den Committee undertaking check-outs to ensure that users have followed instructions and emptied cupboards and fridges/freezers of food. Vermin control contract in place with Grahams Environmental with monthly checks and control undertaken. Arrangements in place with Angus Council for the regular collection of waste from the site. | 3 | 2 | 6 | Checks to be undedrtaken at every check-out | Ladenford Den Committee | Every checkout
14 | Pedestrian / Vehicle conflict | 3 | 4 | 12 | There is a gate at the car park to stop cars entry to drive. This gate should be closed but not locked when the site is in use and cars restricted unless otherwise essential. A 5mph speed limit sign is in place. | 3 | 2 | 6 | Annual review | Ladenford Den Committee | Annually in April
15 | Use / storage of equipment | 3 | 3 | 9 | Users advised to store heavy equipment at low levels and use the trolley in the camp store / 2 people when moving heavy objects. All equipment is regularly inspected and replaced if damaged. Procedure is in place for any defects found to be reported to Ladenford Den Committee. | 3 | 2 | 6 | Review at each check-out | Ladenford Den Committee | Each check-out
16 | Cleaning | 4 | 3 | 12 | Those hiring hall asked to leave it clean. Cleaning contract also in place. | 2 | 3 | 6 | Continue to monitor work of cleaners | Ladenford Den Committee | Each checkout plus review of cleaning contract at each Ladenford Den meeting.

## Safeguarding and compliance
| Risk Area | L | I | IR | Controls already in place | L | I | MR | Actions 2026/7 | Who | Review | COMMENTS
SAFEGUARDING and COMPLIANCE
17 | Camps and sleepovers with children | 3 | 3 | 9 | Leaders must follow child:adult ratios and have completed health forms and all other required qualifications. A safety briefing must be carried out by the leader at the start of the event including details evacuation procedure, evacuation routes, assembly points and use of alarm breakpoints. The leader should contact the fire brigade in event of a fire/rescue situation. The group leader is responsible for the welfare of the children. | 3 | 2 | 6 | Annual review | Ladenford Den Committee | Annually in April
18 | Safeguarding | 2 | 4 | 8 | Ladenford Den Committee members to have appropriate Safe Space qualifications. | 2 | 3 | 6 | County to notify Chair of anyone who has not completed training | County / Chair of Ladenford Den | On-going

## External
| Risk Area | L | I | IR | Controls already in place | L | I | MR | Actions 2026/7 | Who | Review | COMMENTS
EXTERNAL
19 | Winds, flooding etc | 3 | 4 | 12 | Lour Estate undertake (quarterly) tree inspection and take remedial action as required. Lour Estate undertake regular inspection of bridges over burn and undertake remedial action as required. | 3 | 3 | 9 | Quarterly checking of paperwork | Ladenford Den Chair | Quarterly

## Regulatory
| Risk Area | L | I | IR | Controls already in place | L | I | MR | Actions 2026/7 | Who | Review | COMMENTS
REGULATORY
20 | Electrical system | 3 | 4 | 12 | EICR testing up to date and PAT testing done on an annual basis. | 3 | 3 | 9 | Electrician has agreed to carry out EICR on 5-yearly basis (next due June 27) Electrician has agreed to carry out PAT testing on an annual basis (next due May 26) | Ladedford Den Committee | Annually in May for PAT testing. June 27 for EICR.
21 | Asbestos Management | 3 | 3 | 9 | Asbestos survey carried out in October 2023. Asbestos detected in all five of the old black toilet cisterns. No further action needed except annual review. | 3 | 3 | 9 | Annual inspection of toilet cisterns every October. Ensure any contractors doing work on the toilets are aware of the survey results. Consider replacing toilet cisterns in the future. | Ladedford Den Committee | Annually in October and report in Asbestos register.

## Income Streams (hidden)
| Risk Area | L | I | IR | Controls already in place | L | I | MR | Actions 2021 | R 2021 | Who | Review
INCOME STREAMS
1

## Completed Risks (hidden)
3 | IT - fail to upgrade connectivity | 4 | 4 | 16 | IT general support contract Additional contracts in place for website, on-line shop, telephony | 3 | 4 | 12 | CEO
4 | Review of sale of Netherurd not properly carried out to ensure proceeds properly distributed and consideration given to facilities for future GGS trainings and events | 0 | 0 | 0 |  | 0 | 0 | 0
4 | Review of media platforms (social media/tv etc) to ensure GGS adapts and changes to meet demand | 0 | 0 | 0 |  | 0 | 0 | 0 |  | I'm not sure this is a risk? Perhaps 'Fail to adapt to changing communication preferences' but I'm still not sure that it is worth including on the register and it isn't emerging. It doessn't fit under any of the other catagories.